## task2
| authentication |  | time
1 | register + event |  | 2 hours
2 | login |  | 45 min
3 | logout |  | 30 min
4 | verify+reset |  | 30min
5 | forgetpassword |  | 30 min
| routes | time
| admin | 15min
| doctor | 15min
| patient | 15min
| auth api | 15min
| admin controller |  | time
1 | changedata |  | 30min
2 | updatedata |  | 30min
3 | show departments |  | 30min
| usercontroller |  | time
1 | show profile |  | 30 min
2 | update profile |  | 30 min
3 | change password |  | 30 min
4 | delete account |  | 30 min

## task3
authentication |  | admin panel
register+user_type | 1 hour | login | 15 min
login | 30 min | logout | 15 min
logout | 30 min | update admin | 15 min
sendotp | 1 hour | doctors+search | 30 min
verifyemail | 1hour | patients+search | 30 min
reset password | 1 hour | updatename | 1 hour
|  | delete user | 1 hour
departments
create | 30 min | Trait
show | 30 min | 15 min
delete | 30 min
update | 30 min | api(admin,front)
index | 30 min | 3 hours
testing+routes |  | search
departments | 3 hour | 45 min

## edittask3
authentication
register+user_type | 1 hour | adminpanel
login | 30 min | login | 15 min
logout | 15 min | logout | 15 min
verifyemail | 15 min
reset password | 1 5 min
crud patient and doctors |  | crud list | 30 min
index | 1.5 hour
update | 30 min | search | 1 hour
delete | 30 min
create | 1.5 hour | edit api/front
show | 1.5 hour | 1 hour
routes | 30 min